## Project View
Project: METAL FRAME GO KART | [5 empty] | Month # | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 16 | 16
[6 empty] | Start Month | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 19 | 19 | 19 | 19 | 20 | 20 | 20 | 20 | 21 | 21 | 21 | 21 | 22 | 22 | 22 | 22 | 23 | 23 | 23 | 23 | 24 | 24
[6 empty] | Month Name | 2012-09-01 | 2012-09-01 | 2012-09-01 | 2012-09-01 | 2012-10-01 | 2012-10-01 | 2012-10-01 | 2012-10-01 | 2012-11-01 | 2012-11-01 | 2012-11-01 | 2012-11-01 | 2012-12-01 | 2012-12-01 | 2012-12-01 | 2012-12-01 | 2013-01-01 | 2013-01-01 | 2013-01-01 | 2013-01-01 | 2013-02-01 | 2013-02-01 | 2013-02-01 | 2013-02-01 | 2013-03-01 | 2013-03-01 | 2013-03-01 | 2013-03-01 | 2013-04-01 | 2013-04-01 | 2013-04-01 | 2013-04-01 | 2013-05-01 | 2013-05-01 | 2013-05-01 | 2013-05-01 | 2013-06-01 | 2013-06-01 | 2013-06-01 | 2013-06-01 | 2013-07-01 | 2013-07-01 | 2013-07-01 | 2013-07-01 | 2013-08-01 | 2013-08-01 | 2013-08-01 | 2013-08-01 | 2013-09-01 | 2013-09-01 | 2013-09-01 | 2013-09-01 | 2013-10-01 | 2013-10-01 | 2013-10-01 | 2013-10-01 | 2013-11-01 | 2013-11-01 | 2013-11-01 | 2013-11-01 | 2013-12-01 | 2013-12-01
STAGE | HOURS | WEEKENDS (FRIDAY-SATURDAY) | Add To Unit Prior | CUMMULITAVE WEEKENDS | Week Start | Week End | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  |  | 1 | 2
BOM Over View | 8 | 0.5 | 1 | 2.5 | 1 | 2 | 1: BOM Over View; 2: BOM Over View
ORDER PARTS | 16 | 1 | 1 | 3.5 | 2 | 3 | 2: ORDER PARTS; 3: ORDER PARTS
CUT TUBING | 16 | 1 | 1 | 4.5 | 3 | 4 | 3: CUT TUBING; 4: CUT TUBING
CUT OUT PLATES | 8 | 0.5 | 1 | 5 | 4 | 5 | 4: CUT OUT PLATES; 5: CUT OUT PLATES
CUT OUT STEERING COMPONENTS | 16 | 1 | 1 | 6 | 5 | 6 | 5: CUT OUT STEERING COMPONENTS; 6: CUT OUT STEERING COMPONENTS
WELD UP FRAME | 18 | 1.125 | 1 | 7.125 | 5 | 7 | 5: WELD UP FRAME; 7: WELD UP FRAME
MOUNT ENGINE | 16 | 1 | 1 | 8.125 | 7 | 8 | 7: MOUNT ENGINE; 8: MOUNT ENGINE
MOUNT REAR AXEL | 8 | 0.5 | 1 | 8.625 | 7 | 8 | 7: MOUNT REAR AXEL; 8: MOUNT REAR AXEL
MOUNT FAB TENSIONER | 8 | 0.5 | 1 | 9.125 | 8 | 9 | 8: MOUNT FAB TENSIONER; 9: MOUNT FAB TENSIONER
MOUNT BRAKES | 6 | 0.375 | 1 | 9.5 | 8 | 9 | 8: MOUNT BRAKES; 9: MOUNT BRAKES
MOUNT PEDALS | 6 | 0.375 | 1 | 9.875 | 8 | 9 | 8: MOUNT PEDALS; 9: MOUNT PEDALS
FAB ACCELERATOR SYSTEM | 8 | 0.5 | 1 | 10.375 | 9 | 10 | 9: FAB ACCELERATOR SYSTEM; 10: FAB ACCELERATOR SYSTEM
CUT OUT SEAT | 8 | 0.5 | 1 | 10.875 | 9 | 10 | 9: CUT OUT SEAT; 10: CUT OUT SEAT
GLUE-FAB SEAT | 8 | 0.5 | 1 | 11.375 | 10 | 11 | 10: GLUE-FAB SEAT; 11: GLUE-FAB SEAT
MOUNT SEAT | 4 | 0.25 | 1 | 11.625 | 10 | 11 | 10: MOUNT SEAT; 11: MOUNT SEAT
FAB MUFFLER | 8 | 0.5 | 1 | 12.125 | 11 | 12 | 11: FAB MUFFLER; 12: FAB MUFFLER
FAB MUFFLER SHIELD | 8 | 0.5 | 1 | 12.625 | 11 | 12 | 11: FAB MUFFLER SHIELD; 12: FAB MUFFLER SHIELD
FINAL ASSEMBLY | 8 | 0.5 | 1 | 13.125 | 12 | 13 | 12: FINAL ASSEMBLY; 13: FINAL ASSEMBLY
TEST | 6 | 0.375 | 1 | 13.5 | 12 | 13 | 12: TEST; 13: TEST
DISSASSEMBLY | 4 | 0.25 | 1 | 13.75 | 12 | 13 | 12: DISSASSEMBLY; 13: DISSASSEMBLY
PAINT | 32 | 2 | 1 | 15.75 | 13 | 15 | 13: PAINT; 15: PAINT
REASSEMBLE | 4 | 0.25 | 1 | 16 | 15 | 16 | 15: REASSEMBLE; 16: REASSEMBLE
FINAL TEST DRIVE | 8 | 0.5 | 1 | 16.5 | 15 | 16 | 15: FINAL TEST DRIVE; 16: FINAL TEST DRIVE
TOTAL HOURS | 232
Total Weekends | 16.5
Copyright GoKartGuru.com Gamble Industries LLC 2012

## Date Table
1 | 2012-01-01
2 | 2012-02-01
3 | 2012-03-01
4 | 2012-04-01
5 | 2012-05-01
6 | 2012-06-01
7 | 2012-07-01
8 | 2012-08-01
9 | 2012-09-01
10 | 2012-10-01
11 | 2012-11-01
12 | 2012-12-01
13 | 2013-01-01
14 | 2013-02-01
15 | 2013-03-01
16 | 2013-04-01
17 | 2013-05-01
18 | 2013-06-01
19 | 2013-07-01
20 | 2013-08-01
21 | 2013-09-01
22 | 2013-10-01
23 | 2013-11-01
24 | 2013-12-01
25 | 2014-01-01
26 | 2014-02-01
27 | 2014-03-01
28 | 2014-04-01
29 | 2014-05-01
30 | 2014-06-01
31 | 2014-07-01
32 | 2014-08-01
33 | 2014-09-01
34 | 2014-10-01
35 | 2014-11-01
36 | 2014-12-01
37 | 2015-01-01
38 | 2015-02-01
39 | 2015-03-01
40 | 2015-04-01
41 | 2015-05-01
42 | 2015-06-01
43 | 2015-07-01
44 | 2015-08-01
45 | 2015-09-01
46 | 2015-10-01
47 | 2015-11-01
48 | 2015-12-01
49 | 2016-01-01
50 | 2016-02-01
51 | 2016-03-01
52 | 2016-04-01
53 | 2016-05-01
54 | 2016-06-01
55 | 2016-07-01
56 | 2016-08-01
57 | 2016-09-01
58 | 2016-10-01
59 | 2016-11-01
60 | 2016-12-01
61 | 2017-01-01
62 | 2017-02-01
63 | 2017-03-01
64 | 2017-04-01
65 | 2017-05-01
66 | 2017-06-01
67 | 2017-07-01
68 | 2017-08-01
69 | 2017-09-01
70 | 2017-10-01
71 | 2017-11-01
72 | 2017-12-01
73 | 2018-01-01
74 | 2018-02-01
75 | 2018-03-01
76 | 2018-04-01
77 | 2018-05-01
78 | 2018-06-01
79 | 2018-07-01
80 | 2018-08-01
81 | 2018-09-01
82 | 2018-10-01
83 | 2018-11-01
84 | 2018-12-01
85 | 2019-01-01
86 | 2019-02-01
87 | 2019-03-01
88 | 2019-04-01
89 | 2019-05-01
90 | 2019-06-01
91 | 2019-07-01
92 | 2019-08-01
93 | 2019-09-01
94 | 2019-10-01
95 | 2019-11-01
96 | 2019-12-01
97 | 2020-01-01
98 | 2020-02-01
99 | 2020-03-01
100 | 2020-04-01
101 | 2020-05-01
102 | 2020-06-01
103 | 2020-07-01
104 | 2020-08-01
105 | 2020-09-01
106 | 2020-10-01
107 | 2020-11-01
108 | 2020-12-01
109 | 2021-01-01
110 | 2021-02-01
111 | 2021-03-01
112 | 2021-04-01
113 | 2021-05-01
114 | 2021-06-01
115 | 2021-07-01
116 | 2021-08-01
117 | 2021-09-01
118 | 2021-10-01
119 | 2021-11-01
120 | 2021-12-01
121 | 2022-01-01
122 | 2022-02-01
123 | 2022-03-01
124 | 2022-04-01
125 | 2022-05-01
126 | 2022-06-01
127 | 2022-07-01
128 | 2022-08-01
129 | 2022-09-01
130 | 2022-10-01
131 | 2022-11-01
132 | 2022-12-01
133 | 2023-01-01
134 | 2023-02-01
135 | 2023-03-01
136 | 2023-04-01
137 | 2023-05-01
138 | 2023-06-01
139 | 2023-07-01
140 | 2023-08-01
141 | 2023-09-01
142 | 2023-10-01
143 | 2023-11-01
144 | 2023-12-01
145 | 2024-01-01
146 | 2024-02-01
147 | 2024-03-01
148 | 2024-04-01
149 | 2024-05-01